Northern Counties Safety Group Ltd.

Temporary Works Policy

28th of May 2013

| Policy Date | Updated by |
| --- | --- |
| May 2012 | C. Penketh |
| May 2013 | C. Penketh |

TEMPORARY WORKS POLICY

To ensure appropriate arrangements are in place to manage temporary works that meet the legal requirements of the Construction (Design and Management) Regulations 2007 and effectively manage the risk in compliance with BS 5975 (Code of Practice for Temporary Works) to ensure all temporary works are planned, designed and inspected.

The Temporary Works Policy requires that the risks and hazards associated with temporary works are identified, classified and controlled. This procedure is intended to ensure compliance with the companies Temporary Works Policy and covers the following:

- The appointment of personnel responsible for identifying, controlling, designing and constructing temporary works.

- Classification of temporary works according to the risk it brings to the public, construction personnel, property and the reputation of the company.

- Management process for temporary works and the procedure for recording each stage in the process.

- The importance of communication between all parties to ensure safe, practicable and economic temporary works solutions.

Temporary works are any temporary arrangement required to construct or access the permanent works, or used to support the permanent works during its construction and/or until it becomes self-supporting. This includes scaffolding, edge protection, propping, falsework, safety nets, staircases, formwork etc.

Temporary Works Designer (TWD) will most likely be from a contractor or specialist design organisation.

Designated Individual (DI) companies who are responsible for temporary works need to appoint a designated individual to establish a temporary works procedure. BS5975 envisages this person to be either the companies engineer or the companies Operations Director.

Temporary Works Co-ordinator (TWC) – this role will usually be carried out by a Contracts Manager or similar, who has been appointed by the DI. Anyone appointed to be the TWC must have revalent experience and training specific to the role of TWC. He is responsible for ensuring that a temporary works design has been provided and that those installing the temporary works have a suitably developed safe system of work (method statement) and has been briefed in the design and the agreed safe system of work.

Temporary Works Supervisor (TWS) – this role will usually be carried out by the site manager / supervisor and will ensure the temporary works are being managed correctly when the temporary works co-ordinator is not on site , again experience and training in supervising general construction activities incl. drainage, falsework, propping, scaffold is required. The TWS supervises the installation and removal of the temporary works, requesting inspection and sign offs at the appropriate stage.

Temporary Works Design Checker(s) (TWDC) – this role will usually be carried out by the site design team to ensure that all designs are suitable. However, if the designs are classed as category 2 or 3 then they should be undertaken by an individual engineer not involved in the project or another external organisation.

To assist with the identification of different types of temporary works, the following temporary works classifications have been colour coded using the traffic light system green, amber and red, with green being lower risk and red being high risk temporary works.

Note: The categories 0 to 3 (below) as quoted are stipulated in BS 5975 (The Temporary Works British Standard) as a means of specifying the level of checks required for temporary works.

Are classified as green and are potentially low risk temporary works. This category will utilise proprietary products and be of simple construction to a standard solution or manufacturer’s assembly guide.

Are classified as amber and represent a medium risk.

Category 1 temporary works need to be designed by a competent person and drawings produced for the installers and erectors.

Are classified as red and have the highest risk they also must be designed by a competent engineer. To ensure that the design has been carried out correctly an independent engineer must be appointed to check the design and sign acceptance of the design and drawings.

See below for a more comprehensive list of the categories and the different types of temporary works under each category.

Are potentially low risk temporary works. In general these are items which can be designed and constructed based on the experience of competent tradesmen following standard solutions, assembly guides and detailed method statements.

Normally this class of temporary works will utilise proprietary products, assembly guides, British Standards, European guidance and be of simple construction to a standard solution.

Examples of temporary works that will normally be Category 0 include:

- Shallow trenches less than 1.2 metres in depth.

- Proprietary shoring systems (trench and drag boxes) less than 2metres deep.

- Tube and Fitting Scaffolds which are “Basic” as defined inTG20:08

- Un-sheeted, tied scaffolds less than 14m high

- Debris netted or sheeted, tied scaffolds less 10m high.

- Formwork less than 1.2 metres in height.

- Edge protection, if a standard solution is available to BSEN13374

- Fences or hoardings up to 1.2 metres high.

- 2 metre high Heras fence panels supported as per Heras erection guide.

- System scaffolds within the parameters of the assembly guide.

- Haki staircases or similar within the parameters of the assembly guide.

- Free standing aluminium access towers erected and used in accordance with the manufacturers recommendations and PASMA guidance.

- Safety nets secured to robust primary members (i.e. hot rolled steel) as per HSG 33 (Safety in Roofwork)

- Internal hoarding systems and temporary partitions not subject to wind or differential air pressure or crowd loading.

- Rubbish chutes and gin wheels within the parameters of the manufacturers guide.

The site management team are responsible for checking that the temporary works method statement and risk assessment are specific to the job. Any assembly guides or manufacturers specification documents quoted must be on site.

Category 1 temporary works are medium risk and require a design and drawing.

The items listed below can present serious risks when designed or installed incorrectly. Category 1 temporary works need to be designed by a competent person and this design and drawing must be checked by the management team.

Examples of temporary works that will normally be Category 1 include:

- Propping to support openings and floors, including needling (Strongboys etc).

- Trench excavations up to 3 metres deep. Also see Category 1 for shoring systems.

- Unsheeted scaffolds whose top lift is higher than 14m.

- Sheeted scaffolds higher than 10m.

- System scaffolds outside the assembly guide documents.

(Continued)

- Free standing buttressed scaffold.

  - Edge Protection which does not have a standard solution to BS EN 13374

- Safety net systems which are not fixed to robust primary members (e.g. cold formed sections) or are of an unusual design.

- Simple bridges with beams and basic scaffold cantilevers.

- Loading Bays and working platforms which require greater loading than 3kN/m2.

- Basic Temporary Roofs. Hoists, mast climbers, etc

- Formwork for concrete walls above 1.2 metres in height.

Category 2 temporary works which are high risk and must be designed by a competent engineer. To ensure that the design has been carried out correctly, an independent engineer must be appointed as the TW Design Checker for these works.

The following is a typical list of Category 2 temporary works:

- All site signboards, hoardings and fencing over 3m in height.

- Open cut excavations greater than 6 metres deep (geotechnical advice should be sought over 3 metre depth)

- Ground support schemes greater than 3 metres deep, including sheet piling and proprietary support systems.

- Permanent ground support systems (secant/diaphragm walls).

- Cofferdams and Caissons.

- All tower crane bases.

- Facade retention schemes

- Large Temporary Roofs.

- Jacking schemes.

- Bridge erection schemes (stability checks)

- Complex structural steelwork and pre-cast concrete erection schemes.

- Formwork for concrete walls, columns, etc higher than 3 metres

- Falsework higher than 3 metres

- All permanent formwork (metal decking etc)

- Hoists, mast climbers, etc

- Network rail or similar high risk environments.

For complex or innovative designs which result in complex sequences of construction, would be classed as very high risk. Category 3 design must be designed by a competent engineer from another organisation and check carried out by a second TW Design Checker.

Category 3 temporary works are similar to the list in Category 2, with the only exception being that the designs are unusual and do not follow conventional methods.

Checking and the Temporary Works Register.

All temporary work schemes must be documented in the temporary works register.

Category 1, 2 & 3 designs must undergo a formal check to ensure that the brief has been met; the design complies with current codes, standards and legislation. In addition, the check should address issues of buildability (including maintenance and dismantling), efficiency, robustness and interaction with other concurrent activities. All Category 2 and 3 temporary works must be checked by an independent engineer and signed off with a secondary check certificate.

CONTROL MEASURES

The control measures required for the safe operation of all temporary works are listed here. The specific details in relation to the controls are contained in procedures which follow.

- The allocation of duties and responsibilities to competent staff for all temporary works activities.

- The formal appointment of persons to carry out individual duties.

- The maintenance of a temporary works register.

- The correct classification and assessment of all temporary works.

- The preparation of the concept and design brief based on hazard identification and risk assessment.

- The formal allocation of individual responsibilities to:

Temporary Works Co-ordinator (TWC)

Temporary Works Designer(s) (TWD)

Temporary Works Design Checker(s) (TWDC)

Temporary Works Supervisor(s) (TWS)

- The checking of all materials for adequacy, prior to erection.

- The formal checking of the temporary works design.

- The thorough inspection of the temporary works arrangement before any works or loadings commence.

- The provision of safe access, egress and protective measures to all:

Elevated areas.

Work areas below ground level.

Routes over and across works.

- Regular inspection and maintenance of temporary works

- Formal confirmation that the temporary works is no longer required so that it can be dismantled.

CHECKING AND INSPECTION OF TEMPORARY WORKS

Checking and inspection are essential at every stage of temporary works, from initial concept, through design stage, to erection, use and dismantling.

RESPONSIBILITY

Responsibility must be allocated by the company for the following key elements of the temporary works usually the responsibility of the Temporary Works Co-ordinator:

- The concept of the scheme.

- The design brief.

- The design - drawings and specification etc.

- Checking of the design.

- Adequacy of materials used.

- Communicating the temporary works details to those who need to know. (e.g. method statements, risk assessments, safety briefings, tool box talk etc)

- Site control of erection, maintenance and dismantling. (Consider SG4:10 to prevent falls during the erection and dismantling of temporary works).

- Inspection and records of the temporary works. (E.g. prior to first use and every 7 days)

- Authority to use the temporary works and completion / dismantle.

# Text boxes

OBJECTIVE

INTRODUCTION

DEFINITION OF TEMPORARY WORKS

PERSONNEL INVOLVED WITH TEMPORARY WORKS

PERSONNEL (continued)

CLASSIFICATIONS OF DIFFERENT TYPES OF TEMPORARY WORKS (TRAFFIC LIGHT SYSTEM)

CATEGORY 0

CATEGORY 0

CATEGORY 1

CATEGORY 2 & 3

CATEGORY 1

CATEGORY 2

CATEGORY 1

CATEGORY 3